## Sheet1
Sprint 2023.03.2
Issue# | Description | Points | Days worked:
2865 | Add feature flag for revamp_my_evidence | 0.5 | 9
2858 | Add table to My Evidence | 1 | Planned points:
2859 | Implement add evidence button on table view | 0.5 | 4
2863 | Implement search | 0.5 | Completed points:
2860 | Implement adding evidence into a collection | 0.5 | 3.5
2862 | Implement deleting an orphaned evidence | 0.5
2862 | Implement deleting an orphaned evidence | 0.5
Sprint 2023.04.1
Issue# | Description | Points | Days worked:
2862 | Implement deleting an orphaned evidence | 0.5 | 9
Planned points:
3.5
Completed points: