## Sheet1
Sprint 2023.03.2
Issue# | Description | Points | Days worked:
2865 | Add feature flag for revamp_my_evidence | 0.5 | 9
2858 | Add table to My Evidence | 1 | Availability:
2859 | Implement add evidence button on table view | 0.5 | 4.5
2863 | Implement search | 0.5 | Planned points:
2860 | Implement adding evidence into a collection | 0.5 | 3.5
2862 | Implement deleting an orphaned evidence | 0.5 | Completed points:
3
Sprint 2023.04.0 Auckland
Issue# | Description | Points | Days worked:
2862 | Implement deleting an orphaned evidence | 0.5 | 9
2861 | Allow sorting | 1 | Availability:
2864 | Allow filtering | 2 | 4
Planned points:
3
Completed points:
1.5
Sprint 2023.04.0 Bristol
Issue# | Description | Points | Days worked:
2864 | Allow filtering on Evidence Type | 2 | 9
3223 | Rename "Delete" to "Move to trash bin" | 0.5 | Availability:
3227 | Add Goals to My Evidence Table | 2 | 4.5
Planned points:
4.5
Completed points:
4.5
Sprint 2023.04.0 Cadiz
Issue# | Description | Points | Days worked:
3225 | Add tooltip on delete option | 0.5 | 7 | *once done with the "Convert My Evidence list to a table" epic move it all to testing and ask Elise to test!!!!!
3230 | Allow users to remove evidence from Collections | 1 | Availability: | asign the epic to elise when doing so
3229 | Disable delete for evidence linked to goals | 0.5 | 4
3226 | Add icons to the actions options in My Evidence page | 0.5 | Planned points:
3222 | Allow filtering by collections | 1 | 3.5
Completed points:
3.5
Sprint 2023.04.0 Donetsk
Issue# | Description | Points
3221 | Allow sorting on feedback status | 1 | Days worked:
3228 | Allow filtering on goals | 0.5 | 9
3224 | Allow filtering by creation date | 2 | Availability:
3411 | Add title and description in my evidence page | 0.5 | 4.5
3410 | Add a tooltip on evidence types | 0.5 | Planned points:
3407 | Goal and collection tags need margin | 0.5 | 6
3408 | Add status color on goal tags | 0.5 | Completed points:
3409 | Add a tooltip for goal tag status | 0.5