## Sheet1
Sprint 2023.03.2
Issue# | Description | Points | Days worked:
2865 | Add feature flag for revamp_my_evidence | 0.5 | 9
2858 | Add table to My Evidence | 1 | Availability:
2859 | Implement add evidence button on table view | 0.5 | 4.5
2863 | Implement search | 0.5 | Planned points:
2860 | Implement adding evidence into a collection | 0.5 | 3.5
2862 | Implement deleting an orphaned evidence | 0.5 | Completed points:
3
Sprint 2023.04.0 Auckland
Issue# | Description | Points | Days worked:
2862 | Implement deleting an orphaned evidence | 0.5 | 9
2861 | Allow sorting | 1 | Availability:
2864 | Allow filtering | 2 | 4
Planned points:
3
Completed points:
1.5
Sprint 2023.04.0 Bristol
Issue# | Description | Points | Days worked:
2864 | Allow filtering on Evidence Type | 2 | 9
3223 | Rename "Delete" to "Move to trash bin" | 0.5 | Availability:
3227 | Add Goals to My Evidence Table | 2 | 4.5
Planned points:
4.5
Completed points:
4.5
Sprint 2023.04.0 C****
Issue# | Description | Points | Days worked:
2862 |  |  | 8
2861 |  |  | Availability:
2864 |  |  | 4
Planned points:
0
Completed points:
0
Sprint 2023.04.0 D****
Issue# | Description | Points | Days worked:
2862 |  |  | 9
2861 |  |  | Availability:
2864 |  |  | 4
Planned points:
0
Completed points:
0